## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Building basic structure of the website (navigation bar completed) | 2 | 2023-12-04 | Firstly, I began the application development process by selecting the components to be used. These components include: Home: This section encompasses various tools such as sorting and filtering options, along with an overview of available houses. Navigation Bar: It includes the company logo and provides links to the Home and About sections. About: component responsible for displaying detailed information about the company. Tools: This component comprises sorting buttons, a search functionality with the ability to filter by text, and a button for users to post new listings. Houses: This section displays a list of available housing options (in the house overview page) HouseDisplay: It manages how each house item is displayed in the overview page. HouseDisplay was made into a separate component as house information displayed in the overview page for each house has identical format. (reducing code duplication) HouseDetail:This is responsible for showing a page when a specific house was clicked by user The initial implementation focused on the Navigation Bar (user story 1). Routes were defined in the router/index.js file, and the navigation bar's texts were linked through router-link tags. At this stage, the Navigation Bar includes routes for Houses (Home page) and About. List of houses are successfully fetched from the API, but they are not displayed in a user friendly manner yet. Axios was used to add API-key in the header and to make a GET request. API key is now hard-coded in the file and not secured butthis will be left like this as people who grade my work need to have access to the key anways.
Showing a list of houses & styling tools section of the website | 3 | 2023-12-04 | User story 2 has also been completed where users can see a list of housings with necessary details. Fetched houses are passed to HouseDisplay component one by one which displays housing information in a user friendly manner (including house photo and details such as address, price etc) Search bar, a button to create a new listing, and sort buttons have been created and styled but do not have any functionality attatched to them yet. FlexBox was used to position items in the direction that I want and align-item:center was often used to vertically (horizontally in case of flex-direction:column) center the flex element.
About page completed | 2 | 2023-12-04 | About page is fully complated (BONUS 5) The "About" text in the navigation bar is now rendered in bold whenever a user is actively viewing the About page. This was done through the utilization of the "router-link-exact-active" class. | x
Styled HouseDetail component, changed navigation bar style and started working on a form to create a new listing | 4 | 2023-12-05 | The HouseDetail page, corresponding to user story 5, has been given a very basic set of styles. I have made a decision to create another component named "HouseInfo" as the layout of the information displayed about the recommended houses shown in the house detail page is identical to the layout used to show available listings on home page. Changed the navigation bar style so that when a user is on a route containing "/houses" (encompassing the home page, create new house page, and house detail page), the text "Houses" in the navigation bar is bold and otherwise "About" text is bold. It used to be the case that text "Houses" in the navigation bar was only bold on home page but it is now also bold when a user is on the creating and editing of listing page and house detail page as well. CreateHouse component was made, which is responsible for showing a form that allows users to make a new house listing. I put gradient background over another background to mimic the given style specification.
HouseStore created using Pinia and implemented form logic | 2 | 2023-12-07 | Created a HouseStore using Pinia. It contains one state which is a list of all houses. The store now includes methods that return a sorted version of the listings. Furthermore, all the API requests (fetching listings, and posting a new listing etc) have been moved to the HouseStore. Other components can initialize the store and call these methods. This reduced code duplication and made sure to put all the logic related to House state in one file. Form logic (for creating and editing a listing) has been created. V-model has been used to dynamically obtain the values of user input.
Deleting and editing website | 2 | 2023-12-07 | Started implementing functionalites to delete and edit website (user story 7). Deleting a listing is completed by creating another action method in the HouseStore, which sends a DELETE request to House API but no confirmation logic is implemented yet. Clicking on editing button now takes a user to an edit page using a router-link. It was made sure that the edit and delete buttons are only available when the particular listing was posted by the user. It used madeByMe property of the listings, and used v-if to display the content only if the house is listed by the user.
Making search functionality and sorting to work | 3 | 2023-12-08 | A user is now able to search a house by its address. (user story 3 ) Custom events have been emitted from Tools Component to the Home component whenever there is a change in input, together with the current value of the input. This value is used to get the number of matched listing, which is then passed to the prop for the Houses component. As for the styling of the search field, I added a search icon by setting the background of the input field. The actual text gained extra padding on the left, leaving some room for the search icon and avoid the icon and the text to overlap. Sorting functionality has also been added (user story 4). It also emits custom event which notifies the parent component (Home component) of any change in the choice of sorting method. This is also then passed as a prop to House component to sort the list of houses by the current sorting method of choice.
Create/edit listing page | 4 | 2023-12-08 | A functionality to add a new listing has been completed. It utilizes v-model to keep track of the user inputs and use them to send a POST request to the remote API. Once successfully created, user is redirected to the house detail page of the listing they just created. (Form validation has not been completed yet) Edit page has also been implemented. When the edit button is clciked, the inputs are fautomatically filled with the current data associated with the selected listing. Since the identical form is used for both craeting and editing a listing, a new component named HouseForm was created which is used by CreateHouse and EditHouse components. "type" is passed as a prop, which can either be "create" or "edit", allowing it to deal with given data properly when the form is submitted.
Code cleanup and made Pinia State persistent | 2 | 2023-12-09 | Some code cleanup has been done and comments have been added. Style guide was used to make the website follow the given style specification. HouseStore states has been made persistant, which means that the states do not become empty every time the page is refreshed. This implies that we do not have to fetch all the houses from remote API everytime a new page is loaded.
My listings and favorite listings | 3 | 2023-12-10 | Logic has been implemented where a user can mark a listing as favorite. (Bonus 1) HouseStore now stores another state which is an array of house ids that user marked as favorites. This was also made to be persistent so that we do not lose track of which house was added as favorites. There is also a heart icon added to the house preview and house detail page, which a user can click to like/unlike the listing. Favorites component was added to display the content. My listing can also be shown now by using .madeByMe property of the houses. (Bonus 3) MyHouses component was added to display the content. Two new items are added in the navigation bar, namely "my listings" and "favorites". A user will be taken to a new page with a list of their own housings and their favorite listings, respectively. The reason for making entirely new pages for these functionalities is to keep the simplicity of the home page and not to crowd it with a lot of functionalities. | x
delete item confirmation popup | 1 | 2023-12-11 | When a user attempts to delete a listing, a popup will be displayed, asking the user to confirm their decision to delete the listing. A new DeletePopup component has been created for this purpose.
Mobile UI created | 3 | 2023-12-11 | Mobile UI has been created using media queries following the mobile style specification. Navigation bar has been shifted to the bottom and the margins around the main contents has been reduced to fit all the information in the screen. Since some of the layouts for mobile devices are quite different from the layout specifications for desktop devices, it was wiser and simpler to write a new HTML template text and hide/show the container depending on the width of the device, rather than changing the already-exisiting styles for Desktop devices to fit the mobile style specifications. This was achieved by using "display: none" to the container and then add "display:block" to inside the media query to display the content when the width of the device is small enough.
Recommendation houses choice | 1 | 2023-12-19 | Three recommended houses are shown in the house detail page. (BONUS 4) These are the three houses that have the closest price to the price of the house that is currently being shown. This choice was made simply because for most people, price is the most important factors when deciding on which house to buy/rent. | x
Validate user inputs | 2 | 2023-12-19 | The user input submitted through the form now goes through validation. Firstly, the system checks whether all the required fiels are filled. Following this, the system ensures the integrity of the inputs by verifying if the inputs are valid. For example, it checks whether numeric inputs, like the price, can be parsed as numbers without problem. If the form validation fails, users will be notified with an error message below the failed input and the border of the input field will become red. Additionally, number inputs are parsed as numbers using parseInt() before POST request is sent to the House API. This adds some flexibility to the user's input. For example, if the user decides to type 60m2 for size instead of just 60, doing parseInt() makes sure that I only take the 60 part and not the unit.
Preview of the house photo | 1 | 2023-12-20 | Implemented a feature which allows users to view the current house photo when they try to edit a listing. This needed to be done as it is not possible to set a default value for a file input for security reasons. Additioinally, I decided to hide the text "no file input" so that the users will not feel like they need to upload their photo again. Furthermore, I changed the validation so that no error message is displayed when the users do not upload any new house image in case they are editing.
Recommendation house link bug fix | 0 | 2023-12-20 | When the user navigates from houses/1 to houses/2, it reuses the same component instance. This means that the URL will get updated, but the content will not be reloaded, meaning that there will be no changes in the displayed data. To combat this, I decided to watch for route changes, and whenever any change is detected, I force reload the page by running window.reload().
General feedback applied | 1 | 2023-12-23 | Migrated from Vue CLI to Vite. This was done following the tutorial (https://vueschool.io/articles/vuejs-tutorials/how-to-migrate-from-vue-cli-to-vite/) <script setup> tag is used as opposed to <script> tag, which allowed me to write a much clearner code.
Styles/formatting/structure feedback incorporated | 2 | 2023-12-25 | The currency formatting has been applied to the prices. There is a filter function created in main.js, which is used in both HouseInfo and HouseDetail components. Max width of the content has been decreased for a larger screen. The action icons of the house detail and the house overview page are now placed in column instead of row. However, for the action icons displayed inside of HousePreview, it was made such that when the width of the screen is very small, they will be placed in row to fit more content within the given width. Styles from the form have been improved, following the style specification given to us. This included the change of font-family for input labels and textarea placeholder and making the input fields border more curvy. Indentation level was made consistent to 2 spaces indentation. The use of axios.defaults.headers.common allowed for setting the request headers for all of the API requests, eliminating the duplicated API keys that I had in my previous impleentation. Furthermore, baseURL and API key has been stored in .env file and is accessed via import.meta.env. <nav> has been used for containing navigation bar content, and <article> has been used to contain a self-contained elements.
Logic feedback applied | 2 | 2023-12-25 | CreateHouse and EditHouse components have been deleted and merged into HouseForm component as my previous implementation had many code duplications in the two components. Type of the form (create or edit) has been passed as a route parameter and this is used with v-if: to display the desired title text and corresponding submit buttons (POST or SAVE button) etc API to get one house by ID is now used to incorporate users who might open the website from the house detail page. (e.g. http://localhost:8080/houses/2) There is no longer a watcher on house detail page that reloads the entire page. Rather, clicking on recommendation items result in updating the house variable used inside of the template to render the content. Together, recommendation list is updated. To rerender HouseInfo component which is used to display recommendation house information, :key has been used and has been set to equal to recommendation house id. This means that everytime there is an update in the recommendation list, the component gets rerendered to display the latest picked house information. Updating a house results in the user being navigated to the house details page. The use of global CSS is minimized.
Total amount of hours | 34